# ER OON Operating Model 2027: Models A, B and C

Oct 9, 2026 · @Kamil Salameh

## Summary

All three models keep 10 full-cycle teams in Lebanon, the same levels, badges and pay bands, and meet the January 1, 2027 deadline, when the IDR Gateway becomes US-only. They differ in how Gateway filing is done.

- Model A (people-first): a 7-person US desk types prepared disputes into the Gateway from ClickUp tickets, in about 47 minutes each.

- Model B (automation-first): Lebanon sends ready-to-file bundles, and a 3-person US desk files them through a form-filling Submission Cockpit, in a target of 10 minutes.

- Model C (guided copy desk, proposed): Lebanon prepares each dispute in the IDR Prep Studio, which mirrors the Gateway page by page and checks every field. A 5-person US desk copies each field into the Gateway with one-click copy buttons and submits it, in a target of 15 minutes.

Against Model A, Model C saves $94,000–114,000 a year today and $328,000–400,000 a year by year two. That is about 70–80% of Model B's saving, without new software or a Gateway approval beyond the onshore rule. No model includes recruiting fees or infrastructure costs: we recruit in-house and run on systems and equipment we already have.

Recommendation: propose Model C. It is ready for January 1 with tools we already have, needs no Gateway approval beyond the onshore rule, keeps a 5-person desk that absorbs absences, and captures most of the saving. Model B stays the long-term option once the Gateway confirms in writing that assisted form filling is allowed.

## At a glance

Model B wins on cost and speed, and Model A on simplicity. Model C is the middle ground: ready on January 1 like Model A, with most of Model B's saving.

|  | Model A: people-first | Model B: automation-first | Model C: guided copy desk (proposed) |
| --- | --- | --- | --- |
| How filing works | US desk types from ClickUp tickets | A Cockpit form filler fills the Gateway; the operator checks and submits | The US desk copies each field from the IDR Prep Studio and submits; no tool touches the Gateway |
| Time per dispute | About 47 minutes | Target of 10 minutes | Target of 15 minutes |
| US desk today | 7: 1 working lead, 6 associates | 3: 1 Submission Lead, 2 Specialists | 5: 1 lead, 4 associates, in two staggered shifts covering 07:00–19:00 Central |
| US desk in year 1 / year 2 | 12 / 18 | 5 / 7 | 8 / 11 |
| US desk cost today | $346,000–421,000 | $206,000–261,000 | $252,000–307,000 |
| Ready for January 1 | Yes | No; runs on Model A's desk until Gate 2 (April 30, 2027) | Yes; the Studio is built and used in the December parallel run |
| Outside approvals | Legal sign-off on the onshore rule | Also written Gateway confirmation that assisted form filling is allowed | Legal sign-off on the onshore rule only |
| Absence cover | One absence removes 1 of 7 | One absence removes 1 of 3 | One absence removes 1 of 5 |
| New software | None | Submission Cockpit and form filler | None; the IDR Prep Studio already exists |
| Lebanon specialists by year two | About 125 | About 102 (AI drafting) | About 125; can add AI drafting later |
| Main risk | Cost grows with volume | Gateway terms; a 3-person desk | Copy errors; Google Workspace must be under a HIPAA BAA before real PHI |
| Lebanon structure | 10 teams, 94 people, bridge night rota | Same, plus a 2-person Automation Cell | Same as Model A |

## Model A: people-first

Model A replaces 12 facility teams with 10 full-cycle teams and moves Gateway entry to a 7-person US desk that types from ClickUp tickets. Lebanon prepares every dispute; the US desk only enters it. The team structure, levels, badges, transition and bridge night rota described here are shared by all three models.

- One owner per account: each RCM Specialist works an account from coding to final payment, replacing the coder, biller and negotiator handoffs.

- Payer portfolios, not facilities: work is balanced by effort in three tiers, and new facilities join existing teams.

- US Gateway Desk: 1 working lead and 6 associates enter prepared ClickUp tickets and make no pricing decisions.

- Bridge night rota: any L2, L3 or L4 holding C2 can opt in. Two members work 16:00–24:00 Beirut each night and share a $30,000 quarterly pool, at $300–3,000 each.

- Careers: L1 RCM Specialist I, L2 RCM Specialist II, L3 Senior Specialist I and L4 Senior Specialist II, earned through nine skill badges in quarterly test windows. L5 Principal is the leadership level for team leads and managers.

- Transition and standards: the top 10% of each role earn their role badges without tests, everyone else tests within 3 months, and the bottom 10% restart at L1. No one's pay goes down. From December 2027, losing 25% of badges at a semiannual review means probation, and 50% means termination.

- Growth: the US desk scales on a backlog trigger, to about 12 people in year one and 18 in year two.

## Model B: automation-first

Model B keeps Model A's teams, levels and pay bands, and cuts the US desk to 3 by sending it ready-to-file bundles instead of tickets.

- Submission Cockpit: a US operator opens a bundle on a company device, a helper fills the Gateway forms, and the operator checks every field and clicks submit personally. It is built in-house on our existing Google Workspace, starting from the IDR Prep Studio.

- Dispute factory in Lebanon: AI drafts packets, medical-necessity reports and offer letters, and specialists approve them. The target is 0.33 specialists per daily visit instead of 0.45.

- Automation Cell: 2 Automation Analysts from current specialists own the templates and AI prompts, and the bridge night rota runs the final bundle check.

- Pay on results: a team gainshare pays 3% of recovery above baseline, capped at 15% of base pay. A bounty board pays for clearing claims over 90 days old.

- 12-hour US day: three staggered shifts cover 7:00–19:00 Central, so work prepared in Lebanon is filed the same day.

- Compliance guardrail: only a US person on a US device acts in the Gateway. There is no mirroring, remote control or unattended submission.

## Model C: guided copy desk (proposed)

Model C keeps Model A's teams, levels and pay bands, and makes US filing faster and safer with a tool we already have, the IDR Prep Studio. No automation ever touches the Gateway.

- IDR Prep Studio: an internal web app on our Google Workspace that mirrors the Gateway page by page, including multiple line-item pages. Lebanon enters every field there, the Studio checks formats and required documents, and it saves a confirmation PDF of the summary page.

- Copy desk: the US operator opens the dispute in the Studio's copy desk, which lists every value in portal order with a Copy button, in the format the Gateway expects. The operator copies each field, uploads the documents, and submits personally.

- 15 minutes per dispute: typing, look-ups and format errors disappear, and the operator only copies, checks and submits.

- 5-person US desk: 1 lead and 4 associates in two staggered shifts covering 07:00–19:00 Central. Two more associates on 3–6 month contracts cover the cutover until Gate C1 on March 15, 2027.

- Compliance: only a US person acts in the Gateway, so only the onshore rule needs legal sign-off. Before real claim data goes into the Studio, Google Workspace must be covered by a HIPAA BAA.

- Path to Model B: if the Gateway later confirms that assisted form filling is allowed, the Cockpit can be added on top of the Studio.

## Cost comparison

Model C costs about $94,000–114,000 a year less than Model A today, and $328,000–400,000 less by year two. Model B saves more, but carries the approval and technology risk. US figures are approximate Texas market rates for direct hires, plus 25% for benefits and payroll taxes; replace them with our own pay offers. No recruiting fees or infrastructure costs are included.

| Annual cost (USD) | Model A | Model B | Model C (proposed) | Model C saves vs A |
| --- | --- | --- | --- | --- |
| US desk today | 7 people: 346,000–421,000 | 3 people with bonus plus AI drafting: 206,000–261,000 | 5 people: 252,000–307,000 | 94,000–114,000 |
| Year 1 (about 4,400 disputes a month) | 12 people: 580,000–707,000 | 5 people plus AI drafting: 331,000–408,000 | 8 people: 393,000–478,000 | 187,000–229,000 |
| Year 2 (about 6,500 disputes a month) | 18 people: 861,000–1,050,000 | 7 people plus AI drafting: 452,000–551,000 | 11 people: 533,000–650,000 | 328,000–400,000 |
| One-time | Paid onboarding: 58,000–70,000 | Same onboarding, plus legal review of the Cockpit (quote needed) | Onboarding 42,000–51,000, plus 2 contract associates to March 15: 35,000–43,000 | — |

Lebanon, all models: the bridge night rota costs up to $120,000 a year from its $30,000 quarterly pool, and advanced-badge allowances run $45–70 per holder a month. Model B adds automation allowances ($2,400 a year), the bounty board and the gainshare, and its AI drafting is targeted to avoid about 23 hires by year two, worth roughly $380,000 a year.

## Advantages and drawbacks

Model A is the simplest way to meet January 1, and Model B the cheapest way to run once it is proven. Model C combines Model A's readiness with most of Model B's saving.

### Model A: people-first

Advantages

- Ready for January 1 with no new software: ClickUp tickets and the deadline engine are all it needs.

- A 7-person US desk absorbs absences, leave and volume spikes.

- Simple to explain and run; the US role is plain data entry and easy to hire for.

- Lower compliance exposure, since only legal sign-off on the onshore rule is needed.

- Pay changes are modest and predictable.

Drawbacks

- Highest running cost, growing almost in step with volume to $861,000–1,050,000 a year by year two.

- About 47 minutes of manual typing per dispute, with more room for entry errors.

- US desk size depends heavily on whether the Gateway allows bulk upload.

- About 23 more Lebanon hires by year two than Model B.

### Model B: automation-first

Advantages

- Saves $140,000–160,000 a year now and $409,000–499,000 by year two, and the gap widens with volume.

- Filing drops to a target of 10 minutes per dispute, and a 12-hour US day files Lebanon's work the same day.

- Two checks before filing: Bundle QA reviews every bundle, and the operator checks every field.

- AI drafting and the determination reader cut Lebanon workload and hiring.

- Gainshare and the bounty board reward recovery and clear aged claims.

- Builds on the IDR Prep Studio and systems we already own, so the up-front cost is small.

Drawbacks

- Depends on the Gateway's terms allowing assisted form filling; without it, most of the US saving disappears.

- A 3-person desk is fragile: one absence removes a third of capacity.

- New software to maintain, and Gateway screen changes can break its field mappings.

- AI drafts need constant specialist review and QA sampling.

- Gainshare could push aggressive settlements if its guardrails slip.

- More change for staff at once, on top of the team restructure.

### Model C: guided copy desk (proposed)

Advantages

- Ready for January 1 with a tool that is already built and tested, the IDR Prep Studio.

- Saves $94,000–114,000 a year now and $328,000–400,000 by year two against Model A.

- Only the onshore rule needs sign-off; no Gateway approval is needed, because a US person enters every field.

- The Studio checks every field and document before the US desk sees the dispute, so errors are caught in Lebanon.

- A 5-person desk covers 12 US hours a day and absorbs an absence.

- Leaves the door open to Model B's Cockpit later, without rework.

Drawbacks

- Saves less than Model B: about 70–80% of its saving.

- Manual copying can still introduce errors, so it needs a per-field checklist and night rota review.

- The Studio stores claim data in Google Sheets and Drive, so Google Workspace must be under a HIPAA BAA first.

- Lebanon spends some extra time entering disputes in the Studio, offset by fewer rejected tickets.

## Risks

Model A carries mainly volume and people risks, Model B adds technology, approval and concentration risks, and Model C adds a copy-accuracy risk that its tooling controls. The people risks of the new levels and standards apply to every model.

| Risk | Model | Likelihood | Impact | Response |
| --- | --- | --- | --- | --- |
| We misread the Gateway's onshore rule | All | Low | High | Legal sign-off before the build; offshore access stays as a fallback until December 19 |
| People see the new levels and tests as a threat | All | Medium | Medium | Top 10% earn badges without tests, protected pay, published criteria, one appeal each, consequences only from December 2027 |
| The badge-loss termination rule is challenged | All | Medium | High | HR and legal review under Lebanese labor law before publication; documented reviews; one appeal |
| We lose IDR experts during the change | All | Medium | High | Retention bonus through January 2028; a Senior Specialist path that doesn't require managing |
| The US desk falls behind as volume grows | A, C | Medium | High | Backlog trigger adds staff within 2 weeks; under C, 2 contract staff stay until Gate C1 |
| Copy errors between the Studio and the Gateway | C | Medium | Medium | Studio validation, a per-field checklist and night rota review; errors under 0.5% at Gate C1 |
| Claim data enters the Studio before a HIPAA BAA | C | Low | High | Google Workspace BAA in place before real PHI goes in |
| One US absence cuts capacity by a third | B | High | High | 2 trained on-call staff, leave rules, kill switch on backlog |
| Gateway terms forbid the form filler | B | Medium | High | Gate 0 checks first; fall back to Model C |
| AI drafts contain errors | B | Medium | High | A specialist approves every draft; QA samples AI output weekly |
| A Gateway screen change breaks the Cockpit | B | Medium | Medium | Analysts fix mappings within 1 day; manual entry is always available |
| Gainshare pushes aggressive settlements | B | Low | Medium | Cap, quality multiplier, unchanged decision rights |

## Recommendation and decisions

Go live on Model C. It meets January 1 with tools we already have, and every step can be reversed toward Model A staffing. Model B stays an option for later.

- October–December 2026: hire 5 permanent US staff and 2 on 3–6 month contracts in-house. Get legal sign-off on the onshore rule and a HIPAA BAA for Google Workspace. Train the desk and the bridge night rota on the IDR Prep Studio.

- December 2026: parallel run in the Studio at 25%, then 50%, then all Gateway work; full cutover on December 19. Rank every member within their role on 2026 KPIs.

- January 1, 2027: the Gateway goes US-only, filed from the Studio by the Model C desk.

- January–March 2027: transition tests; the 10 teams launch.

- Gate C1, March 15: 15 minutes or less per dispute, errors under 0.5% and no missed deadlines for 4 weeks. The contracts end and the desk runs at 5.

- April 1: new levels take effect, with raises for anyone moving up.

- Later, optional: if the Gateway confirms in writing that assisted form filling is allowed, pilot Model B's Cockpit on top of the Studio and follow Model B's gates.

Kill switches: we add staff back toward Model A's size if any of these happens:

- The backlog stays above 1 business day for 5 days in a row.

- A deadline is missed because of the desk or a copy error.

- Errors stay above 1% for 2 weeks.

The contract staff can be extended, and in-house recruiting keeps a bench of pre-screened candidates, so more people can start within 2 weeks. Manual entry from ClickUp tickets always stays available.

Decisions requested:

- ☐ Approve Model C: a 5-person US desk filing from the IDR Prep Studio, plus 2 contract staff until Gate C1, hired in-house from October.

- ☐ Approve the HIPAA BAA for Google Workspace and the legal review of the onshore rule.

- ☐ Approve the shared levels, badges, transition plan and bridge night rota, as set in the Badges, Levels and Transition appendix.

- ☐ Keep Model B as a later option, to be considered only after the Gateway confirms in writing that assisted filling is allowed.