# ER OON Operating Model 2027: Model A vs Model B

Oct 9, 2026 · @Kamil Salameh

## Summary

Both models keep 10 full-cycle teams in Lebanon and meet the January 1, 2027 deadline, when the IDR Gateway becomes US-only. They differ in how Gateway filing is done. Model A (people-first) hires a 7-person US Gateway Desk that types prepared disputes into the Gateway. Model B (automation-first) has Lebanon deliver ready-to-file bundles and AI drafts, so a 3-person US desk files them through a Submission Cockpit.

Model B saves about $140,000–160,000 a year today and $409,000–499,000 a year by year two. In exchange, it depends on new software, a legal and Gateway-terms check, and a very small US team. Neither model includes recruiting fees or infrastructure costs: we recruit in-house and run on systems and equipment we already have.

Recommendation: go live on January 1 with Model A, then earn Model B in stages. Pilot the Cockpit in February and step down to 3 US staff only after its gates pass. If a gate fails, we stay on Model A at no extra cost.

## At a glance

Model B wins on cost, speed and coverage; Model A wins on readiness, resilience and simplicity.

|  | Model A: people-first | Model B: automation-first | Edge |
| --- | --- | --- | --- |
| Lebanon structure | 10 full-cycle teams, 94 people, plus a 2-lead bridge shift | Same 10 teams; 4 existing staff form an Automation Cell, including the 2 bridge leads | Even |
| US Gateway desk | 7: 1 working lead, 6 associates, typing from ClickUp tickets | 3: 1 Submission Lead, 2 Specialists, filing from bundles in a Cockpit | B |
| Total headcount today | 101 | 97 | B |
| Filing time per dispute | About 47 minutes | Target of 10 minutes | B |
| US hours covered | One US day shift; bridge shift 12:00–20:00 Beirut | 12 hours, 7:00–19:00 Central, in 3 staggered shifts | B |
| Use of AI | Medical-necessity reports with an approved LLM tool | Also drafts packets and offers, and reads determinations overnight | B |
| Lebanon specialists by year two | About 125 | About 102 (23 fewer hires) | B |
| New software | None; configuration in ClickUp | Submission Cockpit and form filler, built in-house | A |
| Ready for January 1 | Yes | No; runs on Model A's desk until Gate 2 (April 30, 2027) | A |
| Outside approvals | Legal sign-off on the onshore rule | Also written confirmation that the Gateway allows assisted form filling | A |
| Absence cover on the US desk | One absence removes 1 of 7 people | One absence removes 1 of 3 people | A |
| Pay extras | Badge allowances, quarterly bonus, bridge incentive | Adds team gainshare, bounty board, automation allowance | Depends |

## Model A: people-first

Model A replaces 12 facility teams with 10 full-cycle teams and moves Gateway entry to a 7-person US desk. Lebanon prepares every dispute; the US desk only enters it. Nobody is laid off and no one's pay goes down.

- One owner per account: each RCM Specialist works an account from coding to final payment, replacing the coder, biller and negotiator handoffs.

- Payer portfolios, not facilities: work is balanced by effort in three tiers, and new facilities join existing teams.

- US Gateway Desk: 1 working lead and 6 associates enter prepared ClickUp tickets and make no pricing decisions. A 2-lead bridge shift (12:00–20:00 Beirut) fixes tickets the same day.

- Careers: one role with four levels (L1–L4) earned through nine skill badges, with specialist pay of $1,000–2,000 a month.

- Growth: the US desk scales on a backlog trigger, to about 12 people in year one and 18 in year two.

## Model B: automation-first

Model B keeps Model A's teams, levels and pay bands, and cuts the US desk to 3 by sending it ready-to-file bundles instead of tickets.

- Submission Cockpit: a US operator opens a bundle on a company device, a helper fills the Gateway forms, and the operator checks every field and clicks submit personally. It is built in-house on our existing Google Workspace, starting from the IDR Prep Studio.

- Dispute factory in Lebanon: AI drafts packets, medical-necessity reports and offer letters, and specialists approve them. The target is 0.33 specialists per daily visit instead of 0.45.

- Automation Cell: 2 Automation Analysts and 2 Bundle QA Leads, all existing staff, own the templates, AI prompts and final check.

- Pay on results: a team gainshare pays 3% of recovery above baseline, capped at 15% of base pay. A bounty board pays for clearing claims over 90 days old.

- 12-hour US day: three staggered shifts cover 7:00–19:00 Central, so work prepared in Lebanon is filed the same day.

- Compliance guardrail: only a US person on a US device acts in the Gateway. There is no mirroring, remote control or unattended submission.

## Cost comparison

Model B costs about $140,000–160,000 a year less at today's volume and $409,000–499,000 less by year two. US figures are approximate Texas market rates for direct hires, plus 25% for benefits and payroll taxes; replace them with our own pay offers. No recruiting fees or infrastructure costs are included, because recruiting is in-house and both models run on systems and equipment we already have.

| Annual cost (USD) | Model A | Model B | Model B saves |
| --- | --- | --- | --- |
| US desk today | 7 people: 346,000–421,000 | 3 people with bonus (194,000–231,000) plus AI drafting (12,000–30,000): 206,000–261,000 | 140,000–160,000 |
| Year 1 (about 4,400 disputes a month) | 12 people: 580,000–707,000 | 5 people plus AI drafting: 331,000–408,000 | 249,000–299,000 |
| Year 2 (about 6,500 disputes a month) | 18 people: 861,000–1,050,000 | 7 people plus AI drafting: 452,000–551,000 | 409,000–499,000 |
| One-time | Paid onboarding, November–December: 58,000–70,000 | The same onboarding, since Model A's desk runs first; plus legal review of the Cockpit (quote needed) | Legal review only |

Lebanon: Model A adds the bridge shift (up to $6,000 a year) and advanced-badge allowances ($45–70 per holder a month). Model B adds automation allowances ($2,400 a year), the bounty board (up to $150 per person a month) and the gainshare, which is funded from recovery above baseline. In return, AI drafting is targeted to avoid about 23 hires by year two, worth roughly $380,000 a year.

## Advantages and drawbacks

Model A is the safer way to meet January 1; Model B is the cheaper and faster way to run once it is proven.

### Model A: people-first

Advantages

- Ready for January 1 with no new software: ClickUp tickets and the deadline engine are all it needs.

- A 7-person US desk absorbs absences, leave and volume spikes.

- Simple to explain and run; the US role is plain data entry and easy to hire for.

- Lower compliance exposure, since only legal sign-off on the onshore rule is needed.

- Pay changes are modest and predictable.

Drawbacks

- Highest running cost, growing almost in step with volume to $861,000–1,050,000 a year by year two.

- About 47 minutes of manual typing per dispute, with more room for entry errors.

- US desk size depends heavily on whether the Gateway allows bulk upload.

- About 23 more Lebanon hires by year two than Model B.

### Model B: automation-first

Advantages

- Saves $140,000–160,000 a year now and $409,000–499,000 by year two, and the gap widens with volume.

- Filing drops to a target of 10 minutes per dispute, and a 12-hour US day files Lebanon's work the same day.

- Two checks before filing: Bundle QA reviews every bundle, and the operator checks every field.

- AI drafting and the determination reader cut Lebanon workload and hiring.

- Gainshare and the bounty board reward recovery and clear aged claims.

- Builds on the IDR Prep Studio and systems we already own, so the up-front cost is small.

Drawbacks

- Depends on the Gateway's terms allowing assisted form filling; without it, most of the US saving disappears.

- A 3-person desk is fragile: one absence removes a third of capacity.

- New software to maintain, and Gateway screen changes can break its field mappings.

- AI drafts need constant specialist review and QA sampling.

- Gainshare could push aggressive settlements if its guardrails slip.

- More change for staff at once, on top of the team restructure.

## Risks

Model A carries mainly volume and people risks; Model B adds technology, approval and concentration risks. The biggest single risk in Model B is that one absence leaves the US desk a third short.

| Risk | Model | Likelihood | Impact | Response |
| --- | --- | --- | --- | --- |
| We misread the Gateway's onshore rule | Both | Low | High | Legal sign-off before the build; offshore access stays as a fallback until December 19 |
| People read new levels as a demotion | Both | Medium | Medium | Provisional levels, protected pay, published criteria, one appeal each |
| We lose IDR experts during the change | Both | Medium | High | Retention bonus through January 2028; an L4 path that doesn't require managing |
| The US desk falls behind as volume grows | A | Medium | High | Backlog trigger adds staff within 2 weeks; bridge leads report it daily |
| One US absence cuts capacity by a third | B | High | High | 2 trained on-call staff, leave rules, kill switch on backlog |
| Gateway terms forbid the form filler | B | Medium | High | Gate 0 checks first; fall back to on-screen copy help and Model A staffing |
| AI drafts contain errors | B | Medium | High | A specialist approves every draft; QA samples AI output weekly |
| A bundle defect spreads to many disputes | B | Low | High | Bundle QA checks every bundle; analysts fix the template, not just the case |
| A Gateway screen change breaks the Cockpit | B | Medium | Medium | Analysts fix mappings within 1 day; manual entry is always available |
| The US team burns out at 40 disputes a shift | B | Medium | Medium | Quarterly bonus, remote work, review of the pace at Gate 2 |
| Gainshare pushes aggressive settlements | B | Low | Medium | Cap, quality multiplier, unchanged decision rights |

## Recommendation and decisions

Start on Model A, then move to Model B only as each gate passes. The January 1 deadline never depends on new software, and every step can be reversed.

- October–December 2026: hire the 7-person US desk in-house on 3–6 month contracts. Get legal sign-off and the Gateway terms check, and start the Cockpit from the IDR Prep Studio.

- Gate 0, November 30: legal and the Gateway terms both say yes. If not, we stay on Model A.

- January 1, 2027: go live on Model A's desk.

- February to mid-March: pilot the Cockpit on 20%, then 50%, of volume.

- Gate 1, March 15: 12 minutes or less per dispute, errors under 0.5%, 98% of bundles right first time, and no missed deadlines.

- March–April: hire 3 permanent US staff in-house and let contracts end one at a time.

- Gate 2, April 30: 4 weeks on 3 people with the backlog under 1 business day.

- May onward: switch on the determination reader, then start gainshare and the bounty board in the third quarter.

Kill switches: we return to Model A staffing if any of these happens:

- The backlog stays above 1 business day for 5 days in a row.

- A deadline is missed because of the desk or a bundle.

- Errors stay above 1% for 2 weeks.

- The Gateway changes its terms or blocks the form filler.

In-house recruiting keeps a bench of pre-screened candidates so 4 people can start within 2 weeks.

Decisions requested:

- ☐ Approve Model A for January 1, with the US desk hired in-house on 3–6 month contracts.

- ☐ Approve building the Cockpit on our existing systems, and the Gate 0 legal and Gateway-terms review.

- ☐ Approve stepping down to Model B's 3-person desk only after Gates 1 and 2 pass.

- ☐ Approve the gainshare and bounty board from the third quarter of 2027, subject to Gate 2.